## ALT
ALTERNATIVE ENERGY DEPARTMENT
RISK REGISTER
[5 empty] | 4TH QUARTER 2023/24FY | [9 empty] | 1ST QUARTER 2024/25FY | [9 empty] | 2ND QUARTER 2024/25FY | [9 empty] | 3RD QUARTER 2024/25FY
Objective | Risk No. | Risk | Causes | Effects | Risk Assessment |  |  |  | Treatment | Opportunities | Action Points | Responsible | Timeline | Areas reviewed by 30/06/2024 | Risk Assessment |  |  |  | Treatment | Opportunities | Action Points | Responsible | Timeline | Areas reviewed by 30/9/2024 | Risk Assessment |  |  |  | Treatment | Opportunities | Action Points | Responsible | Timeline | Areas reviewed by 30/12/2024 | Risk Assessment |  |  |  | Treatment | Opportunities | Action Points | Responsible | Timeline | Areas reviewed by 28/02/2025 | Risk Assessment
[5 empty] | Likelyhood | Impact | Score | Overall rating | [6 empty] | Likelyhood | Impact | Score | Overall rating | [6 empty] | Likelyhood | Impact | Score | Overall rating | [6 empty] | Likely hood | Impact | Score | Overall rating | [6 empty] | Likely hood | Impact | Score | Overall rating | Status | Evidence
To increase the Corporation contribution of offgrid energy from 10.85MW to 18.85MW in 2028 for Environmental sustainability | REREC/AE/2024/01 | Inability to achieve increase in the Corporation contribution of offgrid energy by 8 MW by 2028 | Lack of approved workplan for the 5 years | 1. Project delays 2. Vandalism 3. Reputation damage to the Corporation 4. Loss of development partners confidence 5. Loss of funding 6. Delayed benefit to the users 7. Legal liabilities | 3 | 5 | 15 | High | Develop a 5 year workplan | N/A | Develop a 5 year workplan 1.Set a team to prepare the plan. 2. Extract all strategies relevant to the department. 3. Allocate responsibilities to staff. 4. Monitor the implementation. 5. Quartely status reports to the board. | Manager,Alternative Energy | 15th February 2024 | 1. Whether a team to prepare the plan was set?.Done 2. Whether you extracted all strategies relevant to the department? Done 3. Whether you allocated responsibilities to the staff?.Done 4. Whether monitoring the implementation was done ?.Done 5.Whether Quartely status reports to the board were done?. Done | 3 | 3 | 9 | High | Develop a 5 year workplan | N/A | Develop a 5 year workplan 1.Set a team to prepare the plan. 2. Extract all strategies relevant to the department. 3. Allocate responsibilities to staff. 4. Monitor the implementation. 5. Quartely status reports to the board. | Manager,Alternative Energy | 30th June 2024 | 4. Whether monitoring the implementation was done ?.Continuous 5.Whether Quartely status reports to the board were done?. Continuous | 2 | 3 | 6 | Moderate | Develop a 5 year workplan | N/A | Develop a 5 year workplan 1.Set a team to prepare the plan. 2. Extract all strategies relevant to the department. 3. Allocate responsibilities to staff. 4. Monitor the implementation. 5. Quartely status reports to the board. | Manager,Alternative Energy | 2024-12-31 | 4. Whether monitoring the implementation was done ?.Continuous 5.Whether Quartely status reports to the board were done?. Continuous | 2 | 3 | 6 | Moderate | Develop a 5 year workplan | N/A | Develop a 5 year workplan 1.Set a team to prepare the plan. 2. Extract all strategies relevant to the department. 3. Allocate responsibilities to staff. 4. Monitor the implementation. 5. Quartely status reports to the board. | Manager,Alternative Energy | 30th March 2025 | 4. Whether monitoring the implementation was done ? 5.Whether Quartely status reports to the board were done?. | 2 | 2 | 4 | Moderate | Done | 1. 5 year Worklan AaatchedMost 2.Most recent Board paper Attached
|  |  | Lack of database of proposed potential project sites | [5 empty] | Develop an updated database of proposed potential project sites. | Collaboration with counties and other stakeholders in identification of project sites | Develop an updated database of proposed potential project sites 1. Identify the sources of potential project sites 2. Develop a database 3. Continuous updates to the database on a quarterly basis. | Manager,Alternative Energy | 30th June 2024 | 1.Whether the sources of potential project sites was identified? Sites identified 2. Whether the database was develpoed? Data base developed 3.Whether there was a Continuous updates to the database on a quarterly basis? yes |  |  |  |  | Develop an updated database of proposed potential project sites. | Collaboration with counties and other stakeholders in identification of project sites | Develop an updated database of proposed potential project sites 1. Identify the sources of potential project sites 2. Develop a database 3. Continuous updates to the database on a quarterly basis. | Manager,Alternative Energy | 30th June 2024 | 3.Whether there was a Continuous updates to the database on a quarterly basis? Continuous |  |  |  |  | Develop an updated database of proposed potential project sites. | Collaboration with counties and other stakeholders in identification of project sites | Develop an updated database of proposed potential project sites 1. Identify the sources of potential project sites 2. Develop a database 3. Continuous updates to the database on a quarterly basis. | Manager,Alternative Energy | 2024-12-31 | 3.Whether there was a Continuous updates to the database on a quarterly basis? Continuous |  |  |  |  | Develop an updated database of proposed potential project sites. | Collaboration with counties and other stakeholders in identification of project sites | Develop an updated database of proposed potential project sites 1. Identify the sources of potential project sites 2. Develop a database 3. Continuous updates to the database on a quarterly basis. | Manager,Alternative Energy | 30th March 2025 | 3.Whether there was Continuous update to the database on a quarterly basis? |  |  |  |  | yes | 1.Attached summary of project progress reports 2.List of proposed identified potential sites Attached
|  |  | Limited access to resource maps | [5 empty] | 1. Sensitize departmental staff on availability of open source resource maps. 2. Regular (annual) consultations with the Ministry requesting available resource maps | N/A | Sensitize departmental staff on availability of open source resource maps. 1.1. Analyse available open source resource maps 1. 2.Sensitization staff on available resource maps in the departmental meetings agenda. Regular (annual) consultations with the Ministry requesting available resource maps 1. Write a letter requesting MoEP for access to resource maps. 2. Follow up with ¦MoEP 3. Attending MoEP events related to resource maps. | Manager,Alternative Energy | 30th June 2024 | Sensitize departmental staff on availability of open source resource maps. 1.1. Whether the available open source resource maps were analysed? Yes 1. 2 Whether the staff Sentitised on available resource maps in the departmental meetings agenda was done?. Yes Regular (annual) consultations with the Ministry requesting available resource maps 2.1. Whetehr the letter requesting MoEP for access to resource maps was written? - Following a discussion with MOEP a letter was not necessary because these rosources are open source 2. Whether a Follow up with ¦MoEP was done ? N/A 3. Whether you attended MoEP events related to resource maps? Yes - including meeting with donor partners - GIZ, World Bank |  |  |  |  | 1. Sensitize departmental staff on availability of open source resource maps. 2. Regular (annual) consultations with the Ministry requesting available resource maps | N/A | Sensitize departmental staff on availability of open source resource maps. 1.1. Analyse available open source resource maps 1. 2.Sensitization staff on available resource maps in the departmental meetings agenda. Regular (annual) consultations with the Ministry requesting available resource maps 1. Write a letter requesting MoEP for access to resource maps. 2. Follow up with ¦MoEP 3. Attending MoEP events related to resource maps. | Manager,Alternative Energy | 30th June 2024 | Sensitize departmental staff on availability of open source resource maps. 2 Whether the staff Sentitised on available resource maps in the departmental meetings agenda was done?. Continuous Regular (annual) consultations with the Ministry requesting available resource maps 2. Whether a Follow up with ¦MoEP was done ? N/A 3. Whether you attended MoEP events related to resource maps? Yes - including meeting with donor partners - GIZ, World Bank |  |  |  |  | 1. Sensitize departmental staff on availability of open source resource maps. 2. Regular (annual) consultations with the Ministry requesting available resource maps | N/A | Sensitize departmental staff on availability of open source resource maps. 1.1. Analyse available open source resource maps 1. 2.Sensitization staff on available resource maps in the departmental meetings agenda. Regular (annual) consultations with the Ministry requesting available resource maps 1. Write a letter requesting MoEP for access to resource maps. 2. Follow up with ¦MoEP 3. Attending MoEP events related to resource maps. | Manager,Alternative Energy | 2024-12-31 | Sensitize departmental staff on availability of open source resource maps. 2 Whether the staff Sentitised on available resource maps in the departmental meetings agenda was done?. Continuous Regular (annual) consultations with the Ministry requesting available resource maps 2. Whether a Follow up with ¦MoEP was done ? N/A 3. Whether you attended MoEP events related to resource maps? Yes - including meeting with donor partners - GIZ, World Bank |  |  |  |  | 1. Sensitize departmental staff on availability of open source resource maps. 2. Regular (annual) consultations with the Ministry requesting available resource maps | N/A | Sensitize departmental staff on availability of open source resource maps. 1.1. Analyse available open source resource maps 1. 2.Sensitization staff on available resource maps in the departmental meetings agenda. Regular (annual) consultations with the Ministry requesting available resource maps 1. Write a letter requesting MoEP for access to resource maps. 2. Follow up with ¦MoEP 3. Attending MoEP events related to resource maps. | Manager,Alternative Energy | 30th March 2025 | Sensitize departmental staff on availability of open source resource maps. 1. 2 Whether the staff Sentitised on available resource maps in the departmental meetings agenda was done?. Yes Regular (annual) consultations with the Ministry requesting available resource maps 2.1. Whether the letter requesting MoEP for access to resource maps was written? - Following a discussion with MOEP a letter was not necessary because these resources are open source 2. Whether a Follow up with ¦MoEP was done ? N/A 3. Whether you attended MoEP events related to resource maps? Yes - including meeting with donor partners - GIZ, World Bank |  |  |  |  | Done | Minutes on Sensitization attached
|  |  | Lack of feasibility studies undertaken | [5 empty] | 1. Ensure that the appropriate feasibility studies are undertaken before project commencement. | 1. Identification of the most suitable and cost effective solutions. 2. Improving the socio-economic wellbeing of the communities directly affected by the projects. | Ensure that the appropriate feasibility studies are undertaken before project commencement. 1.Ensure project management teams are constituted. 2. Identify projects that need feasibility studies. 3. Develop ToRs for feasibility studies. 4. Undertake feasiibility studies . 5. Develop reports | Manager,Alternative Energy | 30th June 2024 | 1. Whether the project management teams were constituted? N/A 2. Whether the projects which needed feasibility studies were indentified? N/A 3. Whether the ToRs for feasibility studies were developed? N/A 4. Did you undertak feasibility studies? N/A 5. Whether the reports were developed? N/A The department has not had a project which requires a feasiblity study |  |  |  |  | 1. Ensure that the appropriate feasibility studies are undertaken before project commencement. | 1. Identification of the most suitable and cost effective solutions. 2. Improving the socio-economic wellbeing of the communities directly affected by the projects. | Ensure that the appropriate feasibility studies are undertaken before project commencement. 1.Ensure project management teams are constituted. 2. Identify projects that need feasibility studies. 3. Develop ToRs for feasibility studies. 4. Undertake feasiibility studies . 5. Develop reports | Manager,Alternative Energy | 30th June 2024 | 1. Whether the project management teams were constituted? N/A 2. Whether the projects which needed feasibility studies were indentified? N/A 3. Whether the ToRs for feasibility studies were developed? N/A 4. Did you undertak feasibility studies? N/A 5. Whether the reports were developed? N/A The department has not had a project which requires a feasiblity study |  |  |  |  | 1. Ensure that the appropriate feasibility studies are undertaken before project commencement. | 1. Identification of the most suitable and cost effective solutions. 2. Improving the socio-economic wellbeing of the communities directly affected by the projects. | Ensure that the appropriate feasibility studies are undertaken before project commencement. 1.Ensure project management teams are constituted. 2. Identify projects that need feasibility studies. 3. Develop ToRs for feasibility studies. 4. Undertake feasiibility studies . 5. Develop reports | Manager,Alternative Energy | 2024-12-31 | 1. Whether the project management teams were constituted? N/A 2. Whether the projects which needed feasibility studies were indentified? N/A 3. Whether the ToRs for feasibility studies were developed? N/A 4. Did you undertak feasibility studies? N/A 5. Whether the reports were developed? N/A The department has not had a project which requires a feasiblity study |  |  |  |  | 1. Ensure that the appropriate feasibility studies are undertaken before project commencement. | 1. Identification of the most suitable and cost effective solutions. 2. Improving the socio-economic wellbeing of the communities directly affected by the projects. | Ensure that the appropriate feasibility studies are undertaken before project commencement. 1.Ensure project management teams are constituted. 3.Identify projects that need feasibility studies. 4. Develop ToRs for feasibility studies. 5. Undertake feasiibility studies and Develop Feasibility Study reports . | Manager,Alternative Energy | 30th March 2025 | 1. Whether the project management teams were constituted? 2. Whether the projects which needed feasibility studies were indentified? 3. Whether the ToRs for feasibility studies were developed? 4. Did you undertak feasibility studies? 5. Whether the reports were developed? |  |  |  |  | Not done | The department has curently not Implemeted projects that require feasibility studies to be conducted in the FY
|  |  | Inadequate budget for the project | [5 empty] | 1. Seek for additional budget 2. Ensure the department is represented during budget-approval process | Alternative follow up methods | Seek for additional budget 1.1 Conclusivly identify departmental activities for budget 1.2 Develop budget for approval 1.3 Do a follow up with finance department to give the actual budget allocated for the department 2. Ensure the department is represented during budget-approval process 2.1 Follow up on representation on the budget-approval process | Manager,Alternative Energy | 30th June 2024 | Seek for additional budget 1.Whether the departmental activities for budget conclusively identified ? Done 1.2 Whether a budget for approval was developed? ? Done 1.3 Whether a follow up with finance department to give the actual budget allocated for the department was done?Done Ensure the department is represented during budget-approval process 2.1 Whether Follow up on representation on the budget-approval process was done?Done |  |  |  |  | 1. Seek for additional budget 2. Ensure the department is represented during budget-approval process | Alternative follow up methods | Seek for additional budget 1.1 Conclusivly identify departmental activities for budget 1.2 Develop budget for approval 1.3 Do a follow up with finance department to give the actual budget allocated for the department 2. Ensure the department is represented during budget-approval process 2.1 Follow up on representation on the budget-approval process | Manager,Alternative Energy | 30th June 2024 | Seek for additional budget Whether a follow up with finance department to give the actual budget allocated for the department was done?yes |  |  |  |  | 1. Seek for additional budget 2. Ensure the department is represented during budget-approval process | Alternative follow up methods | Seek for additional budget 1.1 Conclusivly identify departmental activities for budget 1.2 Develop budget for approval 1.3 Do a follow up with finance department to give the actual budget allocated for the department 2. Ensure the department is represented during budget-approval process 2.1 Follow up on representation on the budget-approval process | Manager,Alternative Energy | 2024-12-31 | Seek for additional budget Whether a follow up with finance department to give the actual budget allocated for the department was done?yes |  |  |  |  | 1. Seek for additional budget 2. Ensure the department is represented during budget-approval process | Alternative follow up methods | Seek for additional budget 1.1 Conclusivly identify departmental activities for budget 1.2 Develop budget for approval 1.3 Do a follow up with finance department to give the actual budget allocated for the department 2. Ensure the department is represented during budget-approval process 2.1 Follow up on representation on the budget-approval process | Manager,Alternative Energy | 30th March 2025 | Seek for additional budget 2.1 Whether Follow up on representation on the budget-approval process was done? |  |  |  |  | Done | Follow up emails on budget approval process
|  |  | Inadequate staff | [5 empty] | 1. Recruitment of additional staff 2. Internal Sourcing of Staff | 1. succession planning 3. Recruitment of additional staff | Recruitment (internal and external) RECRUITMENT OPTION 1. Undertake skills gap analysis 2.Write a memo to HR on the required staff in the department for recruitment 3. Follow up the HR request INTERNAL STAFF SOURCING OPTION 1. Source staff within the directorate or in the Corporation who can be transfered to Alternative Energy department 2. Discuss with the relevant HODs on the possibilities of internal transfers 3. Discuss with the relevant staff on the possibilities of transfrering to Alternative Energy department 4. Write an internal Memo to HR on the possibility of transfer 5. Make a follow up of the HR Memo at least on quarterly basis | Manager,Alternative Energy | 30th June 2024 | RECRUITMENT OPTION 1. Were the skills gap analysis undertaken? Done 2. Whether a memo to HR on the required staff in the department for recruitment was done? An email done with staff requirement 3. Whether a follow up to the HR was done? Done INTERNAL STAFF SOURCING OPTION 1. Whether staff within the directorate or in the Corporation who can be transfered to Alternative Energy department were sourced? Yes, received 2 staff 2. Whethe there was discussion with the relevant HODs on the possibilities of internal transfers? Yes 3. Whether there was discussion with the relevant staff on the possibilities of transfrering to Alternative Energy department? Yes 4. Whetther the internal Memo to HR on the possibility of transfer was written? Yes 5. Whether a follow up tothe HR Memo at least on quarterly basis was done? Yes |  |  |  |  | 1. Recruitment of additional staff 2. Internal Sourcing of Staff | 1. succession planning 3. Recruitment of additional staff | Recruitment (internal and external) RECRUITMENT OPTION 1. Undertake skills gap analysis 2.Write a memo to HR on the required staff in the department for recruitment 3. Follow up the HR request INTERNAL STAFF SOURCING OPTION 1. Source staff within the directorate or in the Corporation who can be transfered to Alternative Energy department 2. Discuss with the relevant HODs on the possibilities of internal transfers 3. Discuss with the relevant staff on the possibilities of transfrering to Alternative Energy department 4. Write an internal Memo to HR on the possibility of transfer 5. Make a follow up of the HR Memo at least on quarterly basis | Manager,Alternative Energy | 30th June 2024 | RECRUITMENT OPTION 3. Whether a follow up to the HR was done? follow up to done INTERNAL STAFF SOURCING OPTION 5. Whether a follow up tothe HR Memo at least on quarterly basis was done? partially done |  |  |  |  | 1. Recruitment of additional staff 2. Internal Sourcing of Staff | 1. succession planning 3. Recruitment of additional staff | Recruitment (internal and external) RECRUITMENT OPTION 1. Undertake skills gap analysis 2.Write a memo to HR on the required staff in the department for recruitment 3. Follow up the HR request INTERNAL STAFF SOURCING OPTION 1. Source staff within the directorate or in the Corporation who can be transfered to Alternative Energy department 2. Discuss with the relevant HODs on the possibilities of internal transfers 3. Discuss with the relevant staff on the possibilities of transfrering to Alternative Energy department 4. Write an internal Memo to HR on the possibility of transfer 5. Make a follow up of the HR Memo at least on quarterly basis | Manager,Alternative Energy | 2024-12-31 | RECRUITMENT OPTION 3. Whether a follow up to the HR was done? follow up to done INTERNAL STAFF SOURCING OPTION 5. Whether a follow up tothe HR Memo at least on quarterly basis was done? partially done |  |  |  |  | 1. Recruitment of additional staff 2. Internal Sourcing of Staff | 1. succession planning 3. Recruitment of additional staff | Recruitment (internal and external) RECRUITMENT OPTION 1. Undertake skills gap analysis 2.Write a memo to HR on the required staff in the department for recruitment 3. Follow up the HR request INTERNAL STAFF SOURCING OPTION 1. Source staff within the directorate or in the Corporation who can be transfered to Alternative Energy department 2. Discuss with the relevant HODs on the possibilities of internal transfers 3. Discuss with the relevant staff on the possibilities of transfrering to Alternative Energy department 4. Write an internal Memo to HR on the possibility of transfer 5. Make a follow up of the HR Memo at least on quarterly basis | Manager,Alternative Energy | 30th March 2025 | RECRUITMENT OPTION 3. Whether a follow up to the HR was done? INTERNAL STAFF SOURCING OPTION 5. Whether a follow up tothe HR Memo at least on quarterly basis was done? |  |  |  |  | Done | internal Departmental Job advertisement attached.
|  |  | Insufficient competencies of staff | [5 empty] | Capacity Buiding | Skilled staff | Capacity building 1. Identify skills gap 2.Include the skills in the training needs in the department. 3.Submit to HR for consideration 4.Train the staff 5. Review the performance in line with training conducted. | Manager,Alternative Energy | 30th June 2024 | Capacity building 1. Whether the skills gap were identified? Yes 2. Whether the skills were Included in the training needs in the department? Yes 3. Whether submittion to the HR for consideration was done? Yes 4. Whether the staff were trained? Yes 5. Whether the performance was Reviewed in line with training conducted? YES |  |  |  |  | Capacity Buiding | Skilled staff | Capacity building 1. Identify skills gap 2.Include the skills in the training needs in the department. 3.Submit to HR for consideration 4.Train the staff 5. Review the performance in line with training conducted. | Manager,Alternative Energy | 30th June 2024 | Capacity building 5. Whether the performance was Reviewed in line with training conducted? continous-performance appraisal includes review on training |  |  |  |  | Capacity Buiding | Skilled staff | Capacity building 1. Identify skills gap 2.Include the skills in the training needs in the department. 3.Submit to HR for consideration 4.Train the staff 5. Review the performance in line with training conducted. | Manager,Alternative Energy | 2024-12-31 | Capacity building 5. Whether the performance was Reviewed in line with training conducted? continous-performance appraisal includes review on training |  |  |  |  | Capacity Buiding | Skilled staff | Capacity building 1. Identify skills gap 2.Include the skills in the training needs in the department. 3.Submit to HR for consideration 4.Train the staff 5. Review the performance in line with training conducted. | Manager,Alternative Energy | 30th June 2024 | Capacity building 5. Whether the performance was Reviewed in line with training conducted? YES |  |  |  |  | Done | Invitation letter and Attendance to Technical Training at Huawei Offices Attached
|  |  | Indequate transport facilitation | [5 empty] | Develop contingency plans for transportation issues | Improvement of project supervision. | Develop contigency plans for transportation issues 1. Share an approved Annual Workplan with the Manager Administration and the relevant GMs at the start of the year. 2.Request for transport facilitation on need basis 3. Request for transport facilitation at least three weeks prior to the planned activities. 4.Explore multiple transportation options including public transportation where necessary during critical exercises. 5. Request for approval of use of personal vehicles where official vehicles are unavailable during times when activities cannot be delayed. 6. Review the implementation of the options regularly to ensure success. | Manager,Alternative Energy | 30th June 2024 | Develop contigency plans for transportation issues 1.Whether an approved workplan with the Manager Administration and relevant GMs was shared at the start of the year. ? 2. Whether request for transportation facilitation was done on need basis? Yes 3. Whether request for transporation facilitation was made at least three weeks to the planned activities? Yes 4. Whether there was exploration of multple transportation option including public transporation where necessary during critical exercises ? Yes 5. Whether request for approval of use of personal vehicles was done where official vehicles are unavailable during times when activities cannot be delayed ? Done on case to case basis 6. whether there was review of implementation option regularly to ensure success? Yes |  |  |  |  | Develop contingency plans for transportation issues | Improvement of project supervision. | Develop contigency plans for transportation issues 1. Share an approved Annual Workplan with the Manager Administration and the relevant GMs at the start of the year. 2.Request for transport facilitation on need basis 3. Request for transport facilitation at least three weeks prior to the planned activities. 4.Explore multiple transportation options including public transportation where necessary during critical exercises. 5. Request for approval of use of personal vehicles where official vehicles are unavailable during times when activities cannot be delayed. 6. Review the implementation of the options regularly to ensure success. | Manager,Alternative Energy | 30th June 2024 | Develop contigency plans for transportation issues 6. whether there was review of implementation option regularly to ensure success? Continous |  |  |  |  | Develop contingency plans for transportation issues | Improvement of project supervision. | Develop contigency plans for transportation issues 1. Share an approved Annual Workplan with the Manager Administration and the relevant GMs at the start of the year. 2.Request for transport facilitation on need basis 3. Request for transport facilitation at least three weeks prior to the planned activities. 4.Explore multiple transportation options including public transportation where necessary during critical exercises. 5. Request for approval of use of personal vehicles where official vehicles are unavailable during times when activities cannot be delayed. 6. Review the implementation of the options regularly to ensure success. | Manager,Alternative Energy | 2024-12-31 | Develop contigency plans for transportation issues 6. whether there was review of implementation option regularly to ensure success? Continous |  |  |  |  | Develop contingency plans for transportation issues | Improvement of project supervision. | Develop contigency plans for transportation issues 1. Share an approved Annual Workplan with the Manager Administration and the relevant GMs at the start of the year. 2.Request for transport facilitation on need basis 3. Request for transport facilitation at least three weeks prior to the planned activities. 4.Explore multiple transportation options including public transportation where necessary during critical exercises. 5. Request for approval of use of personal vehicles where official vehicles are unavailable during times when activities cannot be delayed. 6. Review the implementation of the options regularly to ensure success. | Manager,Alternative Energy | 30th March 2025 | Develop contigency plans for transportation issues 1.Whether an approved workplan with the Manager Administration and relevant GMs was shared at the start of the year. ? 2. Whether request for transportation facilitation was done on need basis? Yes 3. Whether request for transporation facilitation was made at least three weeks to the planned activities? Yes 4. Whether there was exploration of multple transportation option including public transporation where necessary during critical exercises ? Yes 5. Whether request for approval of use of personal vehicles was done where official vehicles are unavailable during times when activities cannot be delayed ? Done on case to case basis 6. whether there was review of implementation option regularly to ensure success? Yes |  |  |  |  | Done | Approval from Administration department to use Alternative means provided
|  |  | Inadequate tools and equipment | [5 empty] | 1.Acquire necessary tools and equipment |  | Acquire necessary tools and equipment 1.Conduct tools & equipment invemstory 2. Tools and equipment specifications 3. Draft memo for approval 4. Liase with procuremennt for tender advert | Manager,Alternative Energy | 30.06.2024 | 1. Whether tools and equipment inventory were conducted? Yes, 2. Whether tools and equipment specifications were developed? Yes 3. Whether a memo for approvals was drafted? Yes 4. Whether there was a liason with procurement department for tender advert? Yes, some of the tools procured, |  |  |  |  | 1.Acquire necessary tools and equipment |  | Acquire necessary tools and equipment 1.Conduct tools & equipment invenstory 2. Tools and equipment specifications 3. Draft memo for approval 4. Liase with procuremennt for tender advert | Manager,Alternative Energy | 30.06.2024 | 4. Whether there was a liason with procurement department for tender advert? Yes, some of the tools procured. Some yet to be procured due to unavailability of budget |  |  |  |  | 1.Acquire necessary tools and equipment |  | Acquire necessary tools and equipment 1.Conduct tools & equipment invenstory 2. Tools and equipment specifications 3. Draft memo for approval 4. Liase with procuremennt for tender advert | Manager,Alternative Energy | 2024-12-31 | 4. Whether there was a liason with procurement department for tender advert? Yes, some of the tools procured. Some yet to be procured due to unavailability of budget |  |  |  |  | 1.Acquire necessary tools and equipment |  | Acquire necessary tools and equipment 1.Conduct tools & equipment invemstory 2. Tools and equipment specifications 3. Draft memo for approval 4. Liase with procuremennt for tender advert | Manager,Alternative Energy | 30.03.2025 | 4. Whether there was a liason with procurement department for tender advert for the goods yet to be procured? |  |  |  |  | Done | List of Request for software and Hardeare for Staff attached
|  |  | Ineffective onboarding of contractors | [5 empty] | 1. Create onboarding checklists with necessary documents and trainings. | Enhanced efficiency of project implementation. | Create onboarding checklists with necessary documents and trainings 1.Develop checklists with necessary documents 2. Provide clear instructions and guidance to contractors on their roles, responsibilities and expectations. 3.Regularly monitor contractor performance and provide feedback | Manager,Alternative Energy | 30th June 2024 | 1. Whether checklists with necessary documents were developed? Yes 2. Whether a clear instructions and guidance to contractors on their roles, responsibilities and expectations. Yes 3.Whether a Regular monitoring of the contractor performance and provision of a feedback was done? Yes |  |  |  |  | 1. Create onboarding checklists with necessary documents and trainings. | Enhanced efficiency of project implementation. | Create onboarding checklists with necessary documents and trainings 1.Develop checklists with necessary documents 2. Provide clear instructions and guidance to contractors on their roles, responsibilities and expectations. 3.Regularly monitor contractor performance and provide feedback | Manager,Alternative Energy | 30th June 2024 | 3.Whether a Regular monitoring of the contractor performance and provision of a feedback was done? Continuos. |  |  |  |  | 1. Create onboarding checklists with necessary documents and trainings. | Enhanced efficiency of project implementation. | Create onboarding checklists with necessary documents and trainings 1.Develop checklists with necessary documents 2. Provide clear instructions and guidance to contractors on their roles, responsibilities and expectations. 3.Regularly monitor contractor performance and provide feedback | Manager,Alternative Energy | 2024-12-31 | 3.Whether a Regular monitoring of the contractor performance and provision of a feedback was done? Continuos. |  |  |  |  | 1. Create onboarding checklists with necessary documents and trainings. | Enhanced efficiency of project implementation. | Create onboarding checklists with necessary documents and trainings 1.Develop checklists with necessary documents 2. Provide clear instructions and guidance to contractors on their roles, responsibilities and expectations. 3.Regularly monitor contractor performance and provide feedback | Manager,Alternative Energy | 30th March 2025 2024 | 3.Whether Regular monitoring of contractor's performance and provision of feedback was done? |  |  |  |  | Yes | 1.Minutes of meeting with Contraactor attached 2.Letter providing feedback to Contractor attached
|  |  | Ineffective contract management | [5 empty] | 1. Development of contract management committee | Enhanced efficiency of project implementation. | Development of contract management committee 1.1 Appoint members of each project management committee with clear ToRs 1.2 Clarify the goals, timeline &scope to the contract management committee 1.3 Establish clear roles for each member of the committee 1.4 Monthly meetings to discuss status, challenges and ways to adress the challenges. | Manager,Alternative Energy | 30th June 2024 | Development of contract management committee 1.1 Whether the members of each project managing committee been appointed with clear Terms of Reference (ToRs)? Yes - KEMP / KOSAP 1.2 Whether clarification of the goals, timeline &scope to the contract management committee was done? Yes 1.3 Whether establishment of clear roles for each member of the committee was done? Yes 1.4 Whether there was Monthly meetings to discuss status, challenges and ways to adress the challenges were done? |  |  |  |  | 1. Development of contract management committee | Enhanced efficiency of project implementation. | Development of contract management committee 1.1 Appoint members of each project management committee with clear ToRs 1.2 Clarify the goals, timeline &scope to the contract management committee 1.3 Establish clear roles for each member of the committee 1.4 Monthly meetings to discuss status, challenges and ways to adress the challenges. | Manager,Alternative Energy | 30th June 2024 | Development of contract management committee 1.4 Whether there was Monthly meetings to discuss status, challenges and ways to adress the challenges were done? |  |  |  |  | 1. Development of contract management committee | Enhanced efficiency of project implementation. | Development of contract management committee 1.1 Appoint members of each project management committee with clear ToRs 1.2 Clarify the goals, timeline &scope to the contract management committee 1.3 Establish clear roles for each member of the committee 1.4 Monthly meetings to discuss status, challenges and ways to adress the challenges. | Manager,Alternative Energy | 2024-12-31 | Development of contract management committee 1.4 Whether there was Monthly meetings to discuss status, challenges and ways to adress the challenges were done? |  |  |  |  | 1. Development of contract management committee | Enhanced efficiency of project implementation. | Development of contract management committee 1.1 Appoint members of each project management committee with clear ToRs 1.2 Clarify the goals, timeline &scope to the contract management committee 1.3 Establish clear roles for each member of the committee 1.4 Monthly meetings to discuss status, challenges and ways to adress the challenges. | Manager,Alternative Energy | 30th March 2025 | Development of contract management committee 1.4 Whether there was Monthly meetings to discuss status, challenges and ways to adress the challenges were done? |  |  |  |  | Yes | Minutes of Project Supervisory Committee Attached
|  |  | Incorrect specifications of quality materials for project implementation | [5 empty] | 1. Review contract documents to ensure compliance with standards and regulations of the project. | 1. Enhanced safety of projects. 2. Enhances project performance. 3. Legal and financial protection | Review contract documents to ensure compliance with standards and regulations of the project. 1.1 Develop a checklist from the contract document 1.2 Conduct inspection 1.3 Prepare inspection report 1.4 Proceed with next actions based of recommendation | Manager,Alternative Energy | 30th June 2024 | Review contract documents to ensure compliance with standards and regulations of the project. 1.1 Whether a checklist was developed from the contract document? Yes 1.2 Whether inspection was conducted? Yes 1.3 Whether inspection report prepared? Yes 1.4 Whether you proceeded with the next actions based on the recommendation? Yes |  |  |  |  | 1. Review contract documents to ensure compliance with standards and regulations of the project. | 1. Enhanced safety of projects. 2. Enhances project performance. 3. Legal and financial protection | Review contract documents to ensure compliance with standards and regulations of the project. 1.1 Develop a checklist from the contract document 1.2 Conduct inspection 1.3 Prepare inspection report 1.4 Proceed with next actions based of recommendation | Manager,Alternative Energy | 30th June 2024 | Review contract documents to ensure compliance with standards and regulations of the project. 1.4 Whether you proceeded with the next actions based on the recommendation? 1.5. Compliance check |  |  |  |  | 1. Review contract documents to ensure compliance with standards and regulations of the project. | 1. Enhanced safety of projects. 2. Enhances project performance. 3. Legal and financial protection | Review contract documents to ensure compliance with standards and regulations of the project. 1.1 Develop a checklist from the contract document 1.2 Conduct inspection 1.3 Prepare inspection report 1.4 Proceed with next actions based of recommendation | Manager,Alternative Energy | 2024-12-31 | Review contract documents to ensure compliance with standards and regulations of the project. 1.4 Whether you proceeded with the next actions based on the recommendation? Yes 1.5. Compliance check-Continous |  |  |  |  | 1. Review contract documents to ensure compliance with standards and regulations of the project. | 1. Enhanced safety of projects. 2. Enhances project performance. 3. Legal and financial protection | Review contract documents to ensure compliance with standards and regulations of the project. 1.1 Develop a checklist from the contract document 1.2 Conduct inspection 1.3 Prepare inspection report 1.4 Proceed with next actions based of recommendation | Manager,Alternative Energy | 30th March 2025 | Review contract documents to ensure compliance with standards and regulations of the project. 1.1 Whether a checklist was developed from the contract document? Yes 1.2 Whether inspection was conducted? Yes 1.3 Whether inspection report prepared? Yes 1.4 Whether you proceeded with the next actions based on the recommendation? Yes | [5 empty] | Site Inspection Report atttached
|  |  | Inacccurate Design | [5 empty] | 1. Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 2. Modify designs based on the site conditions | 1. Improving the quality and reliability of projects. 2. Reduction of risks and uncertainties of projects. | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Procure appropriate software and digital tools 1.2 Train staff on procured softwares and digital tools 1.3 Evaluate effectiveness of softwares procured Modify designs based on the site conditions 2.1 Analyse project sites against designs of the project 2.2 Develop report 2.3 Implement recommendations of the report. | Manager,Alternative Energy | 30th June 2024 | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Whether you procured appropriate software and digital tools? 1.2 Were the staff trained on procured softwares and digital tools? 1.3 Whether Evaluattion of effectiveness of softwares procured was done ? 2. Modify designs based on the site conditions 2.1 Whether the project sites against designs of the project were analysed? 2.2 Whether the report was Developed? 2.3 Whether the recommendations of the report were created? Softwares identified, to be requested in next funding cycle |  |  |  |  | 1. Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 2. Modify designs based on the site conditions | 1. Improving the quality and reliability of projects. 2. Reduction of risks and uncertainties of projects. | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Procure appropriate software and digital tools 1.2 Train staff on procured softwares and digital tools 1.3 Evaluate effectiveness of softwares procured Modify designs based on the site conditions 2.1 Analyse project sites against designs of the project 2.2 Develop report 2.3 Implement recommendations of the report. | Manager,Alternative Energy | 30th June 2024 | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Whether you procured appropriate software and digital tools? Budget issue 1.2 Were the staff trained on procured softwares and digital tools? 1.3 Whether Evaluattion of effectiveness of softwares procured was done ? 2. Modify designs based on the site conditions 2.1 Whether the project sites against designs of the project were analysed? 2.2 Whether the report was Developed? 2.3 Whether the recommendations of the report were created? Softwares identified, to be requested in next funding cycle |  |  |  |  | 1. Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 2. Modify designs based on the site conditions | 1. Improving the quality and reliability of projects. 2. Reduction of risks and uncertainties of projects. | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Procure appropriate software and digital tools 1.2 Train staff on procured softwares and digital tools 1.3 Evaluate effectiveness of softwares procured Modify designs based on the site conditions 2.1 Analyse project sites against designs of the project 2.2 Develop report 2.3 Implement recommendations of the report. | Manager,Alternative Energy | 2024-12-31 | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Whether you procured appropriate software and digital tools? Budget issue 1.2 Were the staff trained on procured softwares and digital tools? 1.3 Whether Evaluattion of effectiveness of softwares procured was done ? 2. Modify designs based on the site conditions 2.1 Whether the project sites against designs of the project were analysed? 2.2 Whether the report was Developed? 2.3 Whether the recommendations of the report were created? Softwares identified, to be requested in next funding cycle |  |  |  |  | 1. Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 2. Modify designs based on the site conditions | 1. Improving the quality and reliability of projects. 2. Reduction of risks and uncertainties of projects. | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Procure appropriate software and digital tools 1.2 Train staff on procured softwares and digital tools 1.3 Evaluate effectiveness of softwares procured Modify designs based on the site conditions 2.1 Analyse project sites against designs of the project 2.2 Develop report 2.3 Implement recommendations of the report. | Manager,Alternative Energy | 30th March 2025 | Use the appropriate software and digital tools to create, update and share designs to prevent inconsistencies. 1.1 Whether you procured appropriate software and digital tools? 1.2 Were the staff trained on procured softwares and digital tools? 1.3 Whether Evaluattion of effectiveness of softwares procured was done ? 2. Modify designs based on the site conditions 2.1 Whether the project sites against designs of the project were analysed? 2.2 Whether the report was Developed? 2.3 Whether the recommendations of the report were created? |  |  |  |  | Yes | Evidence of request for procurement of softwares Attached
[13 empty] | PREPARED BY | [6 empty] | APPROVED BY
[13 empty] | Joselyne Masiga |  | Sign……………………….. |  |  |  |  | Eng. Jonathan Mbutu |  | Sign…………………………………
[13 empty] | Renewable Energy Officer | [6 empty] | Manager, Alternative Energy
[13 empty] | Rural Electrification & Renewable Energy Corporation | [6 empty] | Rural Electrification & Renewable Energy Corporation
[13 empty] | Date: ……………. /March 2025 | [6 empty] | Date: …………………./ March 2025